## Sheet1
Team Member | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-01 | 2024-06-02 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-08 | 2024-06-09 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-15 | 2024-06-16 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-22 | 2024-06-23 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-06-29 | 2024-06-30 | 2024-07-01
Eleanor | 2024-05-29: Group meeting and planning session. Time spent: 30 minutes; 2024-05-31: Worked on project definition scope and management approach sections. Time spent: 1 hour; 2024-06-02: Worked on project definition background and description and final editing. Time spent: 2 hours; 2024-06-04: Preparation for stand up 1. Time spent: 30 mins; 2024-06-05: Team meeting. Time spent: 1 hour; 2024-06-06: Set up project repository, found list of news sources to be scraped and sorted out a short list for testing. Time spent: 2 hours; 2024-06-07: Checked news sources for paywalls and how to get around them. Time spent: 1 hour; 2024-06-09: Worked on sprint 1 user scenarios, user profiles, and use case diagrams. Time spent: 3 hours; 2024-06-11: Worked on journal entry 1. Time spent: 1 hour; 2024-06-12: Team meeting, worked on new user stories. Time spent: 1 hour; 2024-06-14: Worked on presentation and sprint deliverable. Time spent: 2 hours; 2024-06-16: Worked on sprint deliverable - progress report discussion. Time spent: 2 hours; 2024-06-17: Worked on/rehearsed for presentation. Time spent: 1 hour; 2024-06-19: Research for condensation method, both online websites and python libraries. Time spent: 1 hour; 2024-06-22: Research into condensation methods and their benefits/drawbacks. Time spent: 2 hours; 2024-06-23: Worked on user stories and use case diagram for deliverable. Time spent: 2 hours; 2024-06-24: Worked on use case diagram for sprint deliverable. Time spent: 2 hours
Yunis | First group meeting preparation. Time spent: 30 mins | Worked on project objective and project assumption section of project def document. Time spent: 1 hour | Worked on project constraints and team organization. Time spent: 1 hour | Project definition group meeting preparation. Time spent: 30 mins | Worked on gantt chart for project schedule. Time spent: 30 mins | None | Preparation for stand up 1. Time spent: 30 mins | Researched on how to use BeautifulSoup library to get content from webpage. Time spent: 2 hours | Hard coding web scraper (for article body contents) for a specific link I chose. Time spent: 1.15 hours | Turn functional hard code into a more automated function. Time spent 1.3 hours | Created google trending news scraper to automate article selection based on trending to ensure. Time spent: 2 hours | Worked on sprint 1 product roadmap and burndown. Time spent: 2 hours | None | None | Worked on fixing product burndown chart. Time Spent: 30 mins | None | None | Worked on integrating the headline and article scrapers, and expanding the capabilities of the article scraper. Time spent: 4 hours | None | Worked on the sprint 2 documentation and project update presentation. Updated project def. Time spent: 3 hours | None | None | None | Worked on Sprint 3 deliverable. Time spent: 0.5 hours | Researched various LLMs to potentially use. Time spent: 2 hours | Researched various LLMs to potentially use. Time spent: 2 hours | Applied feedback to Sprint 3 deliverable. Time spent: 1 hour
Jack | 2024-05-29: Group meeting and planning session. Time spent: 30 minutes; 2024-06-02: Planning and writing the project definition document. Time spent: 2 hours; 2024-06-05: Team meeting. Time spent: 1 hour; 2024-06-06: Looking at different methods of scraping headlines and determining which method yeilds the results most aligned with our goals. Time spent: 1.5 hours; 2024-06-07: Determining the best method for scraping data from Google Trends, and coding the web scraper. Time spent: 2 hours; 2024-06-09: Worked on sprint 1 product backlog and coding a web scraper for articles related to a headline. Time spent: 4 hours; 2024-06-12: Fixed incorrect url output from headline scraper. Time spent: 1 hour; 2024-06-15: Worked on integrating the headline and article scrapers, and expanding the capabilities of the article scraper. Time spent: 4 hours; 2024-06-17: Sprint 2 documentation and presentation. Time spent: 2.5 hours; 2024-06-20: Reaserch and implementation of nlp and specifically summarization models. Time spent: 5 hours; 2024-06-23: Improvements to condenser code and documentation. Time spend: 1 hour; 2024-06-24: Writing documentation and updating issue log. Time spent: 0.5 hours