## Sheet1
Team Member | time axis 2024-05-29 to 2024-08-06
Eleanor | 2024-05-29: Group meeting and planning session. Time spent: 30 minutes; 2024-05-31: Worked on project definition scope and management approach sections. Time spent: 1 hour; 2024-06-02: Worked on project definition background and description and final editing. Time spent: 2 hours; 2024-06-04: Preparation for stand up 1. Time spent: 30 mins; 2024-06-05: Team meeting. Time spent: 1 hour; 2024-06-06: Set up project repository, found list of news sources to be scraped and sorted out a short list for testing. Time spent: 2 hours; 2024-06-07: Checked news sources for paywalls and how to get around them. Time spent: 1 hour; 2024-06-09: Worked on sprint 1 user scenarios, user profiles, and use case diagrams. Time spent: 3 hours; 2024-06-11: Worked on journal entry 1. Time spent: 1 hour; 2024-06-12: Team meeting, worked on new user stories. Time spent: 1 hour; 2024-06-14: Worked on presentation and sprint deliverable. Time spent: 2 hours; 2024-06-16: Worked on sprint deliverable - progress report discussion. Time spent: 2 hours; 2024-06-17: Worked on/rehearsed for presentation. Time spent: 1 hour; 2024-06-19: Research for condensation method, both online websites and python libraries. Time spent: 1 hour; 2024-06-22: Research into condensation methods and their benefits/drawbacks. Time spent: 2 hours; 2024-06-23: Worked on user stories and use case diagram for deliverable. Time spent: 2 hours; 2024-06-24: Worked on use case diagram for sprint deliverable. Time spent: 2 hours; 2024-06-26: Group meeting and planning for sprint. Time spent: 1 hour; 2024-06-27: Diagram and user stories for sprint. Time spent: 1 hour; 2024-06-30: Website design planning, research into HTML and libraries. Time spent: 2 hours; 2024-07-03: Group meeting and planning. Time spent: 1 hour; 2024-07-04: Create first draft of website in HTML to match the design. Time spent: 3 hours; 2024-07-07: Powerpoint slides and info for presentation. Time spent: 2 hours; 2024-07-10: Group meeting, research into displaying CSV files in HTML - use a JavaScript function to call from the website. Time spent: 4 hours; 2024-07-12: Finalize first draft of the website with the JavaScript functions. Time spent: 2 hours; 2024-07-14: Finalize information in sprint deliverable, ensure all user stories were implemented and use case diagram is accurate. Time spent: 2 hours; 2024-07-17: Set up use case diagram and user stories for sprint deliverable. Time spent: 2 hours; 2024-07-18: Continue work on displaying CSV in HTML/JavaScript - use jQuery for pulling CSV. Time spent: 2 hours; 2024-07-19: Finalize this website version without using React, prepare for final version of website. Time spent: 3 hours.; 2024-07-21: Group meeting: finalize web design and ensure all functonalities work. Time spent: 1.5 hours; 2024-07-23: Synchronization in front end website versions. Time spent: 2 hours.; 2024-07-27: Implement additional UX principles into website design, ensure a smooth user experience. Time spent: 2 hours; 2024-07-28: Finish sprint deliverables and update the documentation for submission. Time spent: 2 hours; 2024-07-29: Finalize HTML website to show the CSV information with JavaScript and CSS manipulation. Time spent: 4 hours; 2024-07-31: Group meeting, established plan for presentation and demos to be given. Time spent: 1 hour; 2024-08-02: Create presentation with slides and outline. Time spent: 1 hour; 2024-08-03: Testing of website and its functionalities. Time spent: .5 hour; 2024-08-05: Update slides, practice for presentation. Time spent: 1 hour
Yunis | 2024-05-29: First group meeting preparation. Time spent: 30 mins; 2024-05-30: Worked on project objective and project assumption section of project def document. Time spent: 1 hour; 2024-05-31: Worked on project constraints and team organization. Time spent: 1 hour; 2024-06-01: Project definition group meeting preparation. Time spent: 30 mins; 2024-06-02: Worked on gantt chart for project schedule. Time spent: 30 mins; 2024-06-03: None; 2024-06-04: Preparation for stand up 1. Time spent: 30 mins; 2024-06-05: Researched on how to use BeautifulSoup library to get content from webpage. Time spent: 2 hours; 2024-06-06: Hard coding web scraper (for article body contents) for a specific link I chose. Time spent: 1.15 hours; 2024-06-07: Turn functional hard code into a more automated function. Time spent 1.3 hours; 2024-06-08: Created google trending news scraper to automate article selection based on trending to ensure. Time spent: 2 hours; 2024-06-09: Worked on sprint 1 product roadmap and burndown. Time spent: 2 hours; 2024-06-10: None; 2024-06-11: None; 2024-06-12: Worked on fixing product burndown chart. Time Spent: 30 mins; 2024-06-13: None; 2024-06-14: None; 2024-06-15: Worked on integrating the headline and article scrapers, and expanding the capabilities of the article scraper. Time spent: 4 hours; 2024-06-16: None; 2024-06-17: Worked on the sprint 2 documentation and project update presentation. Updated project def. Time spent: 3 hours; 2024-06-18: None; 2024-06-19: None; 2024-06-20: None; 2024-06-21: Worked on Sprint 3 deliverable. Time spent: 0.5 hours; 2024-06-22: Researched various LLMs to potentially use. Time spent: 2 hours; 2024-06-23: Researched various LLMs to potentially use. Time spent: 2 hours; 2024-06-24: Applied feedback to Sprint 3 deliverable. Time spent: 1 hour; 2024-06-25: Preparation for stand up. Time spent: 30 mins; 2024-07-01: Preparation for stand up. Time spent: 30 mins; 2024-07-02: Worked on initial website design in Figma. Time spent: 3 hours; 2024-07-06: Iterated on first draft of website. Time spent: 2 hours; 2024-07-09: Preparation for stand up. Time spent: 30 mins; 2024-07-15: sprint deliverable work. Time spent: 1.5 hours; 2024-07-16: Preparation for stand up. Time spent: 30 mins; 2024-07-23: Preparation for stand up. Time spent: 30 mins; 2024-07-28: sprint deliverable work. Time spent: 2 hours; 2024-07-30: Preparation for stand up. Time spent: 30 mins; 2024-08-02: Updated documentation. Time spent 2 hours; 2024-08-06: Worked on fixing up presentation. Time spent: 2 hours
Jack | 2024-05-29: Group meeting and planning session. Time spent: 30 minutes; 2024-06-02: Planning and writing the project definition document. Time spent: 2 hours; 2024-06-05: Team meeting. Time spent: 1 hour; 2024-06-06: Looking at different methods of scraping headlines and determining which method yeilds the results most aligned with our goals. Time spent: 1.5 hours; 2024-06-07: Determining the best method for scraping data from Google Trends, and coding the web scraper. Time spent: 2 hours; 2024-06-09: Worked on sprint 1 product backlog and coding a web scraper for articles related to a headline. Time spent: 4 hours; 2024-06-12: Fixed incorrect url output from headline scraper. Time spent: 1 hour; 2024-06-15: Worked on integrating the headline and article scrapers, and expanding the capabilities of the article scraper. Time spent: 4 hours; 2024-06-17: Sprint 2 documentation and presentation. Time spent: 2.5 hours; 2024-06-20: Reaserch and implementation of nlp and specifically summarization models. Time spent: 5 hours; 2024-06-23: Improvements to condenser code and documentation. Time spend: 1 hour; 2024-06-24: Writing documentation and updating issue log. Time spent: 0.5 hours; 2024-06-30: Worked on chucking and summarization stages. Time spent: 6 hours; 2024-07-01: Worked on improving summary output content. Time spent: 5 hours; 2024-07-04: Experimentation with different small language models. Phi-3 mini-4k model provides best quality/time trade-off. Time spent: 7.5 hours; 2024-07-08: ironed out minor kinks in summarization, and prepared presentation. Time spent: 3 hours; 2024-07-10: Implemented necessary tensor functions to allow Phi-3 to run on Apple GPU: Time spent 3.5 hours; 2024-07-13: Updated Phi-3 language model prompt inorder to produce better summaries with less bias and repetative information. Time spent: 2 hours; 2024-07-15: Work on sprint documentation. Time spent 1 hour; 2024-07-19: Work on fixing redirect url retrevial, as google news url redirect method was changed. Time spend 5 hours; 2024-07-20: Updating webscraper to collect a wider variety of trending headlines, and split the headlines into categories. Time spend 6 hours; 2024-07-21: Front end development. Time spent 2 hours; 2024-07-25: Begin react front end. Time spent: 2 hour; 2024-07-27: Coding react web page, implementing categories feature in web scraper and summarizer, and fixing issues with web scraper. Time spent: 9 hours; 2024-07-29: Implementing categories in front end, making links to original articles clickable, finding and constructing alternate condensation method as the original had begun hallucenating very frequently for an unknown reason. Time spent: 11 hours; 2024-07-31: Added summarized headline functionality instead of using the headline of the top article. Time spent: 4 hours; 2024-08-02: Implemented external models through groq cloud, worked on prompting llama-3.1-70b-versatile model. Time spent: 4.5 hours; 2024-08-04: Solving issue with google news redirect, created process to avoid automated search detection by google, removing closely related stories, correcting summary grammar. Time spent: 10 hours; 2024-08-05: minor changes to summarization process, fix cosmetic issues with frontend, automating running the backend every 24 hours, touch up code, write documentation. Time spent: 7 hours; 2024-08-06: Finished code, created summarizer flowchart, created summarizer demo video, finishing toches on presentation. Time spent: 3.5 hours